## Cover Page
AI Course
Capstone Project
Work Breakdown Structure
For students
ⓒ2023 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today |  | 2026-04-13
Project Team Name |  | NMJ Innovation Team
Project Topic |  | ParaTalent Hub
Task |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4
[8 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20
[8 empty] | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03
1. Data Acquisition & Preprocessing |  |  | 2025-03-09 | 2025-03-16 | Ignacio, Juan, Miguel |  | Done | bar: 2025-03-09 to 2025-03-16
| 1.1 Web Scraping lexi.global |  | 2025-03-09 | 2025-03-11 | Ignacio, Juan, Miguel | scraper.py & scraper_datos_final.py | Done | bar: 2025-03-09 to 2025-03-11
| 1.2 Data Analysis Formulario CPE |  | 2025-03-09 | 2025-03-13 | Ignacio, Juan, Miguel | data_analysis_CPE | Done | bar: 2025-03-09 to 2025-03-13
| 1.3. Data Consolidation |  | 2025-03-16 | 2025-03-16 | Ignacio, Juan, Miguel | data_analysis_CPE | Done | bar: 2025-03-16
| 1.3 Inverse Mapping for Sports |  | 2025-03-16 | 2025-03-16 | Ignacio, Juan, Miguel | mapa_deportes.json | Done | bar: 2025-03-16
2. Backend & RAG Infrastructure |  |  | 2025-03-16 | 2025-03-23 | Ignacio, Juan, Miguel |  | Done | bar: 2025-03-16 to 2025-03-23
| 2.1. Embedding Generation |  | 2025-03-16 | 2025-03-20 | Ignacio, Juan, Miguel | cerebro.py | Done | bar: 2025-03-16 to 2025-03-20
| 2.2. Vector DB Setup (FAISS) |  | 2025-03-17 | 2025-03-20 | Ignacio, Juan, Miguel | cerebro.py | Done | bar: 2025-03-17 to 2025-03-20
| 2.3. LLM Integration (OpenAI) |  | 2025-03-19 | 2025-03-23 | Ignacio, Juan, Miguel | 1_Admin.py | Done | bar: 2025-03-19 to 2025-03-23
3. Advanced Logic & ML Models |  |  | 2025-03-23 | 2025-03-30 | Ignacio, Juan, Miguel |  | Done | bar: 2025-03-23 to 2025-03-30
| 3.1. RAG Improvements. |  | 2025-03-23 | 2025-03-25 | Ignacio, Juan, Miguel | 1_Admin.py | Done | bar: 2025-03-23 to 2025-03-25
| 3.2. Data sourcing for predictive models |  | 2025-03-23 | 2025-03-25 | Ignacio, Juan, Miguel |  | Done | bar: 2025-03-23 to 2025-03-25
| 3.2. Talent Detection (Random Forest) |  | 2025-03-26 | 2025-03-30 | Ignacio, Juan, Miguel | RF Model | Done | bar: 2025-03-26 to 2025-03-30
| 3.3. Deep Learning (MLP Network) |  | 2025-03-26 | 2025-03-30 | Ignacio, Juan, Miguel | MLP Model | Done | bar: 2025-03-26 to 2025-03-30
4. Frontend & Deployment |  |  | 2025-03-23 | 2025-03-31 | Ignacio, Juan, Miguel | MVP | Done | bar: 2025-03-23 to 2025-03-31
| 4.1. Athlete Portal (Streamlit) |  | 2025-03-23 | 2025-03-31 | Ignacio, Juan, Miguel | Home.py | Done | bar: 2025-03-23 to 2025-03-31
| 4.2. Admin Dashboard |  | 2025-03-23 | 2025-03-31 | Ignacio, Juan, Miguel | 1_Admin.py | Done | bar: 2025-03-23 to 2025-03-31
| 4.3. Final Integration & Testing |  | 2025-03-30 | 2025-03-31 | Ignacio, Juan, Miguel |  | Done | bar: 2025-03-30 to 2025-03-31
5. Final Report & PowerPoint |  |  | 2025-03-31 | 2025-04-03 | Ignacio, Juan, Miguel |  | Done | bar: 2025-03-31 to 2025-04-03
| 5.1. Final Report |  | 2025-03-31 | 2025-04-03 | Ignacio, Juan, Miguel |  | Done | bar: 2025-03-31 to 2025-04-03
| 5.2. PowerPoint |  | 2025-03-31 | 2025-04-03 | Ignacio, Juan, Miguel |  | Done | bar: 2025-03-31 to 2025-04-03